P032 - Garden Fleet 01 Schedule

Schedule

  - Organisation Overview

    - Phase 1- Port

      - Legal Setup

      - Token IEO

      - Port Buildout (Palawan)

    - Phase 2 - Fleet

      - Fleet Deployment

      - Initial Cleanup

      - Initial Reforestation

    - Phase 3 - Community

      - Community Integration

      - Dashboard Launch

      - Service Expansion

    - Phase 4 (2027): Government ESG contract

      - Contract 1

        - Onboarding

        - Auditing

      - Contract 2

        - Onboarding

        - Auditing

      - Contract 3

        - Onboarding

        - Auditing

    - Phase 5 (2028–2029): Regional scaling

      - Port 2 Established

      - Port 3 Established

      - Port 4 Established

  - Operational Overview

    - Plastic Recycling Project

      - Setup & Planning (May–June 2025)

        - Land acquisition (3000–5000 sq ft)

        - Permitting and licensing

        - Machinery procurement and vendor agreements

        - Staff recruitment and training

      - Collection & Warehousing (July 2025 onward)

        - Deploy bins (50–100 public locations)

        - Launch community awareness drives

        - Activate mobile collection vans

        - Hire and deploy 4–6 field staff

      - Sorting & Storage (July 2025 onward)

        - Set up covered sorting area with color-coded tables

        - Manual/semi-automated sorting (PET, HDPE, LDPE, etc.)

        - Implement daily hygiene, fire, and pest control protocols

      - Recycling & Manufacturing (August 2025 onward)

        - Install and operate shredders, washers, dryers, moulders

        - Produce recycled pellets, bricks, planters, buckets

        - Quality control and packaging setup

      - Marketing & Sales (August 2025 onward)

        - Launch online store (Instagram, Facebook, WhatsApp)

        - Build partnerships with eco-stores and construction companies

        - Run 'Trash to Treasure' awareness campaigns

        - Implement Return & Recycle programs and loyalty discounts

    - Milestone Events

      - Project Launch (May 2025)

      - Bin Network Deployment (July 2025)

      - First 10 Tons Processed (by September 2025)

      - First Product Launch and Sale (October 2025)

      - Financial Review and Adjustment (November 2025)